## Summary
KPI | Value
Total Tasks | 10
Completed Tasks | 3
In Progress Tasks | 3
Not Started Tasks | 4
Overall % Complete | 46%
Project Start Date | 2025-01-06
Project End Date | 2025-06-27
Total Duration (Days) | 172
Overall Status | On Track

## Task List
Task | Owner | Start Date | End Date | Status | % Complete
Discovery & Research | Sarah Chen | 2025-01-06 | 2025-01-24 | Completed | 100%
Requirements Gathering | Mike Johnson | 2025-01-20 | 2025-02-07 | Completed | 100%
UX Wireframes | Priya Patel | 2025-02-03 | 2025-02-21 | Completed | 100%
Technical Architecture | David Kim | 2025-02-10 | 2025-03-07 | In Progress | 75%
Backend Development | David Kim | 2025-03-03 | 2025-04-18 | In Progress | 50%
Frontend Development | Priya Patel | 2025-03-17 | 2025-05-02 | In Progress | 35%
API Integration | Mike Johnson | 2025-04-21 | 2025-05-16 | Not Started | 0%
QA Testing | Sarah Chen | 2025-05-05 | 2025-05-30 | Not Started | 0%
Beta Launch | Alex Torres | 2025-06-02 | 2025-06-13 | Not Started | 0%
GA Release | Alex Torres | 2025-06-16 | 2025-06-27 | Not Started | 0%

## Gantt Timeline
Task | Start Date | End Date | Duration (Days) | % Complete | Progress Bar (20 blocks = 100%)
Discovery & Research | 2025-01-06 | 2025-01-24 | 18 | 100% | ████████████████████
Requirements Gathering | 2025-01-20 | 2025-02-07 | 18 | 100% | ████████████████████
UX Wireframes | 2025-02-03 | 2025-02-21 | 18 | 100% | ████████████████████
Technical Architecture | 2025-02-10 | 2025-03-07 | 25 | 75% | ███████████████░░░░░
Backend Development | 2025-03-03 | 2025-04-18 | 46 | 50% | ██████████░░░░░░░░░░
Frontend Development | 2025-03-17 | 2025-05-02 | 46 | 35% | ███████░░░░░░░░░░░░░
API Integration | 2025-04-21 | 2025-05-16 | 25 | 0% | ░░░░░░░░░░░░░░░░░░░░
QA Testing | 2025-05-05 | 2025-05-30 | 25 | 0% | ░░░░░░░░░░░░░░░░░░░░
Beta Launch | 2025-06-02 | 2025-06-13 | 11 | 0% | ░░░░░░░░░░░░░░░░░░░░
GA Release | 2025-06-16 | 2025-06-27 | 11 | 0% | ░░░░░░░░░░░░░░░░░░░░
TOTAL DURATION (Days) |  |  | 172